## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: 5 |  |  |  |  | Arpita Kumari | akumar71@uic.edu
[5 empty] | Isaac Kim | ikim32@uic.edu
[5 empty] | Lydia Tse | ltse5@uic.edu
[5 empty] | Neil Thimmaiah | npemma2@uic.edu
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
Setup server & client and allow multiple clients to connect to the server |  | Lydia | N/A | Read through Socket.io and Node.JS documentation | 1. Implement HTTP server 2. Instantiate IO object whenever client connects to waiting room webpage 3. Create handlers for established connections and disconnections | N/A
Implement User Interface Designs for Webpages |  | Isaac, Lydia, Neil, Arpita | N/A | 1. Read about Node.js, React.js 2. Learn how to implement UI elements 3. Prototype for the necessary user interfaces using Figma | 1. Create elements using React.js for each of prototyped pages 2. Make the Interfaces user friendly 3. Debug the code for GUI Elements. | N/A
Implement buttons to play again or to quit: If Play Again button is chosen, player will be pushed to the end of the waiting room queue(the queue that is used to hold the new players) If Quit button is chosen, disconnects player from the game and close the connection of that player to the socket |  | Neil | N/A | 1.Create the buttons for each player to quit. 2. Try creating the button to play again if the first round works fine. | 1. Make sure implementation of all buttons work fine. 2. Check to make sure there is no error whils closing the connection of a player using quit button. 3. Play again should reset everything for that specific player. | N/A
Develop the set of words to use in game |  | Isaac & Lydia | N/A | 1. Review documentation for Oxford Dictionary API | 1. Develop filtering logic to filter words that are 5 - 7 letters in length and whose letters only produce one valid word | N/A
Use 4 variables to keep track of the score of each player |  | Neil, Arpita | N/A | 1. Implement the 4 variables for each of the players. | 1. Make sure that the variables are not getting mixed up and each one corresponds to their respective players | N/A
Implement Waiting room logic |  | Lydia, Neil | N/A | 1. Create a queue that holds all of the players in the order of descending wait time | 1. Test the queue implementation to ensure that waiting room allows players waiting the longest to enter the next available game | N/A
Use a time function on the server and calculate the time it took for winner to unscramble word |  | Neil, Isaac | N/A | 1. Implement the time function for each of the 4 players 2.Exploring how to use Node.js, React 3. code a few small sample programs to see how these frameworks work. 4. pseudo code winner mechanics game logic | 1. Check to make sure the timer function is working well. 2. Required pausing should be working well too (when a player finished unscrambling the word, stop the time) 3. Debug and test this code thoroughly to check it is working | N/A
Use a boolean flag to tell the server that the client has done unscrambling the word and pause the time function for that player. Do the same for the other 3 players and check which player is the least and that player is the winner of the round (the fastest time to solve) |  | Neil, Arpita | N/A | 1. Add a Boolean flag (4 flags) 2. Implement a way to keep track of the time of all the time limits of all the players | 1. Check to make sure that the boolean flag works correctly 2.Check to make sure that the least time is the one which being allocated as the winner. 3. Timer should pause every time a player unscrambles the word. | N/A
Use the timer module to have a max time limit for a game. |  | Isaac, Neil | N/A | 1. Implement setTimeout() and pass it a function that will be activated to end the game. | 1. Make the code for the function that ends a game. 2. Debug to make sure a game ends for each possible game situation. | N/A